## Project Plan
PROJECT TITLE |  | Payroll Management System |  | TEAM NAME |  | Programming Pangolins
PROJECT MANAGER |  | Ryan Porter |  | PROJECT START DATE |  | 2022-09-26 |  | 0
Team Members: Blake Humes, Brooks Robinson, Ryan Porter, Evan Slominski
WBS | TASK TITLE | TASK DESCRIPTION | DEPENDENCIES | TASK OWNER | PCT OF TASK COMPLETE | SCHEDULED START | SCHEDULED FINISH | ACTUAL START | ACTUAL FINISH | FINISH VARIANCE | DURATION in days | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
[12 empty] | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12
1 | Planning | The first stage of the project. In here, we will decide the schedule and roles. | None |  | 100% | 2022-09-26 | 2022-10-08 | 2022-09-26 | 2022-10-09 | -1 | 10 | ftr | fntr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
1.1 | Create Project Plan | Create the project plan (this sheet). | None | Everyone | 100% | 2022-09-26 | 2022-10-07 | 2022-09-26 | 2022-10-05 | -4 | 8 | ftr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
1.1.1 | Create Excel Sheet | Create the Excel sheet. | None | Ryan | 100% | 2022-09-26 | 2022-09-26 | 2022-09-26 | 2022-09-26 |  | 1 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
1.1.2 | Discuss and Decide on Project Tasks | Discuss and decide on the tasks that will be used. | 1.1.1 | Everyone | 100% | 2022-09-26 | 2022-10-05 | 2022-09-26 | 2022-10-05 |  | 8 | ftr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
1.2 | Complete Role Assignment | Decide the roles which everyone will have. Done in this Excel document in the "Roles" sheet. | 1.1.1 | Everyone | 100% | 2022-09-26 | 2022-10-03 | 2022-09-26 | 2022-10-03 |  | 6 | ftr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
1.2.1 | Generate List of Roles | Generate a list of all the roles that may be needed. | None | Everyone | 100% | 2022-09-26 | 2022-10-02 | 2022-09-26 | 2022-10-03 | 0 | 6 | ftr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
1.2.2 | Assign Roles | Discuss and assign the roles that will be used. | 1.2.1 | Everyone | 100% | 2022-10-02 | 2022-10-05 | 2022-09-28 | 2022-10-03 | -4 | 4 | fntr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
1.3 | Turn in Project Plan | Turn in this document to the DropBox. | 1.1, 1.2 | Ryan | 100% | 2022-10-05 | 2022-10-07 | 2022-10-08 | 2022-10-08 | 0 | 0 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
1.4 | Complete Peer Review | Complete and turn in the peer review for this part. | 1.4 | Everyone | 100% | 2022-10-07 | 2022-10-08 | 2022-10-08 | 2022-10-09 | -1 | 0 | entr | fntr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2 | Analysis | The second stage of the project. In this, we will determine the requirements and refine/group them. | 1 |  | 100% | 2022-10-06 | 2022-10-24 | 2022-10-06 | 2022-10-24 |  | 13 | entr | ftr | ftr | ftr | entr | entr | entr | entr | entr | entr | entr | entr
2.1 | Determine Requirements | Determine all the requirements that will be needed and group them. | None | — | 100% | 2022-10-06 | 2022-10-13 | 2022-10-06 | 2022-10-19 | 4 | 10 | entr | ftr | fntr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.1.1 | Brainstorm Requirements | In a group session and alone, determine as many requirements as possible. | None | Everyone | 100% | 2022-10-06 | 2022-10-10 | 2022-10-06 | 2022-10-12 | 2 | 5 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.1.2 | Refine Requirements | Make the requirements clear, unambiguous, consistent, prioritized, and verifiable. | 2.1.1 | Everyone | 100% | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-17 | 4 | 4 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.1.3 | Group Requirements | Group the requirements into sections: functional, nonfunctional, MoSCoW, etc. as needed. | 2.1.2 | Everyone | 100% | 2022-10-11 | 2022-10-12 | 2022-10-17 | 2022-10-19 | 5 | 3 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.1.4 | Complete Misc. Requirement Tasks | Any other requirement tasks that may be needed. If one group in 2.1.3 does not have any requirements, come up with a few here. | 2.1.3 | Everyone | 100% | 2022-10-11 | 2022-10-12 | 2022-10-17 | 2022-10-19 | 5 | 3 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.2 | Develop Use Cases | Develop the use cases for some of the high-level business processes. | 2.1 | — | 100% | 2022-10-12 | 2022-10-20 | 2022-10-12 | 2022-10-19 | -3 | 6 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.2.1 | Determine Use Cases to Use | Determine which processes will get use cases. | None | Everyone | 100% | 2022-10-12 | 2022-10-13 | 2022-10-12 | 2022-10-17 | 2 | 4 | entr | entr | fntr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.2.2 | Create Use Cases | Type up the use cases in the document with the predefined format. | 2.2.1 | Evan, Ryan | 100% | 2022-10-13 | 2022-10-19 | 2022-10-13 | 2022-10-19 |  | 5 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.2.3 | Review Use Cases | Someone reviews the use cases for accuracy, grammar, and clarity. | 2.2.2 | Brooks, Blake | 100% | 2022-10-19 | 2022-10-20 | 2022-10-19 | 2022-10-20 |  | 2 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.3 | Develop User Stories | Develop user stories for some of the high-level business processes. | 2.1 | — | 100% | 2022-10-12 | 2022-10-19 | 2022-10-12 | 2022-10-19 |  | 6 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.3.1 | Determine General Stories | Determine which processes will get user stories. | None | Everyone | 100% | 2022-10-12 | 2022-10-13 | 2022-10-12 | 2022-10-17 | 2 | 4 | entr | entr | fntr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.3.2 | Create User Stories | Type up the user stories in the document with the predefined format. | 2.3.1 | Brooks, Blake | 100% | 2022-10-13 | 2022-10-19 | 2022-10-13 | 2022-10-19 |  | 5 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.3.3 | Review User Stories | Someone reviews the user stories for accuracy, grammar, and clarity. | 2.3.2 | Evan, Ryan | 100% | 2022-10-19 | 2022-10-20 | 2022-10-19 | 2022-10-20 |  | 2 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.4 | Turn in Project Requirements | Turn in this document to the DropBox. | 2.1, 2.2 ,2.3 | Ryan | 100% | 2022-10-21 | 2022-10-23 | 2022-10-21 | 2022-10-22 | -1 | 1 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
2.5 | Complete Peer Review | Complete and turn in the peer review for this part. | 2.4 | Everyone | 100% | 2022-10-23 | 2022-10-24 | 2022-10-22 | 2022-10-24 |  | 1 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
3 | Design | In the 3rd stage, we will develop the designs for the parts of the systems. | 2 |  | 100% | 2022-10-17 | 2022-11-07 | 2022-10-20 | 2022-11-07 |  | 13 | entr | entr | entr | ftr | ftr | ftr | entr | entr | entr | entr | entr | entr
3.1 | Develop Class Diagram | Develop a class diagram for the system. | None | Evan, Ryan | 100% | 2022-10-17 | 2022-10-25 | 2022-10-26 | 2022-11-04 | 8 | 8 | entr | entr | entr | etr | fntr | entr | entr | entr | entr | entr | entr | entr
3.2 | Develop Use-Case Diagram | Develop a use-case diagram for the system. | None | Brooks | 100% | 2022-10-17 | 2022-11-02 | 2022-10-20 | 2022-11-04 | 2 | 12 | entr | entr | entr | ftr | ftr | entr | entr | entr | entr | entr | entr | entr
3.3 | Develop Activity Diagram(s) | Develop an activity diagram(s) for some of the activities of the system. | None | Brooks | 100% | 2022-10-17 | 2022-11-02 | 2022-10-20 | 2022-11-04 | 2 | 12 | entr | entr | entr | ftr | ftr | entr | entr | entr | entr | entr | entr | entr
3.4 | Determine Hardware Specifications & Coding Guidelines | Determine the standard environment in which the program will run and the coding styles. | None | Everyone | 100% | 2022-10-17 | 2022-11-02 | 2022-10-24 | 2022-11-04 | 2 | 10 | entr | entr | entr | etr | ftr | entr | entr | entr | entr | entr | entr | entr
3.5 | Develop User Interface Diagrams | Develop UI diagrams for the system. | None | Evan | 100% | 2022-10-17 | 2022-11-02 | 2022-10-26 | 2022-11-04 | 2 | 8 | entr | entr | entr | etr | ftr | entr | entr | entr | entr | entr | entr | entr
3.6 | Develop Report Diagrams | Develop report diagrams (NACHA, pay stubs) for the system. | None | Ryan | 100% | 2022-10-17 | 2022-11-02 | 2022-10-23 | 2022-11-04 | 2 | 10 | entr | entr | entr | etr | ftr | entr | entr | entr | entr | entr | entr | entr
3.7 | Develop Method Specifications | Develop a few method specifications. | 3.1 | Ryan | 100% | 2022-10-25 | 2022-11-02 | 2022-10-26 | 2022-11-04 | 2 | 8 | entr | entr | entr | entr | ftr | entr | entr | entr | entr | entr | entr | entr
3.8 | Develop Database Specifications | Determine the database design: tables, keys, etc. | None | Blake | 100% | 2022-10-17 | 2022-11-02 | 2022-10-26 | 2022-11-04 | 2 | 8 | entr | entr | entr | etr | ftr | entr | entr | entr | entr | entr | entr | entr
3.9 | Turn in High & Low Level Designs | Turn in these documents to the DropBox. | 3.1-3.8 | Ryan | 100% | 2022-11-04 | 2022-11-06 | 2022-11-06 | 2022-11-06 |  | 0 | entr | entr | entr | entr | entr | etr | entr | entr | entr | entr | entr | entr
3.1 | Complete Peer Review | Complete and turn in the peer review for this part. | 3.9 | Everyone | 100% | 2022-11-06 | 2022-11-07 | 2022-11-06 | 2022-11-07 |  | 1 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
4 | Implementation | In the 4th part, we will start programming. | 3 |  | 100% | 2022-10-17 | 2022-12-05 | 2022-10-05 | 2022-12-01 | -4 | 42 | entr | fntr | fntr | ftr | ftr | ftr | ftr | ftr | ftr | etr | entr | entr
4.1 | Setup Version Control | Set up GitHub. | None | Ryan | 100% | 2022-10-17 | 2022-11-06 | 2022-10-05 | 2022-10-05 | -24 | 1 | entr | entr | entr | etr | etr | etr | entr | entr | entr | entr | entr | entr
4.2 | Setup Environment | Set up the coding environment, which is VS. | None | Everyone | 100% | 2022-10-17 | 2022-11-06 | 2022-10-17 | 2022-11-02 | -4 | 13 | entr | entr | entr | entr | ftr | entr | entr | entr | entr | entr | entr | entr
4.3 | Setup Bug Tracker | Set up the bug tracker to report and resolve bugs. | None | Ryan | 100% | 2022-10-17 | 2022-11-06 | 2022-10-21 | 2022-10-21 | -12 | 1 | entr | entr | entr | etr | etr | etr | entr | entr | entr | entr | entr | entr
4.4 | Develop the UIs | Setup, program, and customize the UIs. | 4.2 | Evan | 100% | 2022-10-30 | 2022-11-07 | 2022-11-07 | 2022-11-30 | 17 | 18 | entr | entr | entr | entr | entr | etr | entr | fntr | fntr | entr | entr | entr
4.5 | Develop the Database | Setup the database and its related components (default queries, keys, etc.). | 4.2 | Blake | 100% | 2022-10-30 | 2022-11-07 | 2022-11-07 | 2022-11-26 | 14 | 15 | entr | entr | entr | entr | entr | etr | entr | fntr | entr | entr | entr | entr
4.6 | Program the Classes and Forms | Program the methods, fields, and constructors for each of the classes and forms. | 4.2 | — | 100% | 2022-10-30 | 2022-11-23 | 2022-11-07 | 2022-11-30 | 5 | 18 | entr | entr | entr | entr | entr | etr | etr | ftr | fntr | entr | entr | entr
4.6.1 | Program the Security Functions | Program needed SHA256 or AES encryption/decryption methods. | None | Ryan | 100% | 2022-10-30 | 2022-11-23 | 2022-11-07 | 2022-11-09 | -12 | 3 | entr | entr | entr | entr | entr | etr | etr | etr | entr | entr | entr | entr
4.6.2 | Program Login Screen | Program the input for the possible logins and verify to see if the information is a valid user or employee. | None | Evan | 100% | 2022-10-30 | 2022-11-23 | 2022-11-07 | 2022-11-30 | 5 | 18 | entr | entr | entr | entr | entr | etr | etr | ftr | fntr | entr | entr | entr
4.6.3 | Program the Payroll Functions | Program the needed functions to generate pay stubs PDFs and NACHA files. | None | Ryan | 100% | 2022-10-30 | 2022-11-23 | 2022-11-07 | 2022-11-22 | -3 | 12 | entr | entr | entr | entr | entr | etr | etr | ftr | entr | entr | entr | entr
4.6.4 | Program General Classes | Program the properties and methods of all the classes. | None | Brooks | 100% | 2022-10-30 | 2022-11-23 | 2022-11-07 | 2022-11-23 |  | 13 | entr | entr | entr | entr | entr | etr | etr | ftr | entr | entr | entr | entr
4.7 | Refactor Code | Refactor any code to clarify and to structure it. | 4.6 | Ryan | 100% | 2022-11-23 | 2022-11-28 | 2022-11-20 | 2022-12-01 | 3 | 9 | entr | entr | entr | entr | entr | entr | entr | entr | fntr | entr | entr | entr
4.8 | Training Documents | Develop training documents and/or videos for the users. | 4.6 | Brooks | 100% | 2022-11-23 | 2022-12-05 | 2022-11-30 | 2022-12-01 | -4 | 2 | entr | entr | entr | entr | entr | entr | entr | entr | etr | etr | entr | entr
5 | Testing | Perform various tests to ensure the system works as expected. | Varies (Mainly 4) |  | 100% | 2022-10-17 | 2022-12-05 | 2022-10-21 | 2022-12-05 |  | 32 | entr | entr | entr | ftr | ftr | ftr | ftr | ftr | ftr | ftr | entr | entr
5.1 | Create Testing Plan Document(s) | Create a document(s) to hold what testing took place and the results. | 3 | Ryan | 100% | 2022-10-17 | 2022-11-01 | 2022-10-21 | 2022-10-21 | -9 | 1 | entr | entr | entr | entr | etr | entr | entr | entr | entr | entr | entr | entr
5.2 | Perform Installation Test(s) | Verify that the installation files work on other computers of the specified hardware. | 4 | Everyone | 100% | 2022-11-28 | 2022-12-05 | 2022-11-30 | 2022-12-05 |  | 4 | entr | entr | entr | entr | entr | entr | entr | entr | entr | ftr | entr | entr
5.3 | Perform System Testing | Perform tests that span the entire system. | 4 | — | 100% | 2022-11-21 | 2022-12-05 | 2022-11-30 | 2022-12-05 |  | 4 | entr | entr | entr | entr | entr | entr | entr | entr | entr | etr | entr | entr
5.3.1 | Create Manual Test Data | Create the test data that is easy to check by hand so that you can verify the system works. | None | Evan, Brooks | 100% | 2022-11-21 | 2022-11-28 | 2022-11-30 | 2022-12-05 | 5 | 4 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
5.3.2 | Test Manual Test Data | Test the data created to verify that it outputs the correct answer. | 5.3.1 | Evan, Brooks | 100% | 2022-11-28 | 2022-12-05 | 2022-11-30 | 2022-12-05 |  | 4 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
5.4 | Complete Unit Testing | This is a wide ranging task and should be done as/before methods are created. Test each method to make sure it does as expected. | 4.6 | Everyone | 100% | 2022-10-30 | 2022-11-28 | 2022-11-07 | 2022-11-30 | 2 | 18 | entr | entr | entr | entr | entr | etr | etr | ftr | ftr | entr | entr | entr
5.5 | Complete Acceptance Testing | Test to ensure that the requirements are met | 4 | Ryan | 100% | 2022-11-28 | 2022-12-05 | 2022-11-30 | 2022-12-02 | -3 | 3 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
6 | Maintenance | In this step, we will develop a maintenance plan. | 4 |  | 100% | 2022-11-28 | 2022-12-05 | 2022-11-28 | 2022-12-05 |  | 6 | entr | entr | entr | entr | entr | entr | entr | entr | entr | ftr | entr | entr
6.1 | Develop Maintenance Plan | Develop a maintenance plan for future versions and any new bugs that are discovered. | None | — | 100% | 2022-11-28 | 2022-12-05 | 2022-11-28 | 2022-12-05 |  | 6 | entr | entr | entr | entr | entr | entr | entr | entr | entr | ftr | entr | entr
6.1.1 | Assign People and Resources | Determine what resources and people will be assigned to this task. | None | Ryan | 100% | 2022-11-28 | 2022-12-05 | 2022-11-28 | 2022-12-05 |  | 6 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
6.1.2 | Determine Next Version Goals | Determine what feature tasks should be added to the program. | None | Ryan | 100% | 2022-11-28 | 2022-12-05 | 2022-11-28 | 2022-12-05 |  | 6 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
6.1.3 | Determine How To Report Bugs | Determine how users or developers will report new bugs. | None | Ryan | 100% | 2022-11-28 | 2022-12-05 | 2022-11-28 | 2022-12-05 |  | 6 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
7 | Wrap-Up | The final part of the project. In this, we will turn in the final deliverable. | 4, 5, 6 |  | 100% | 2022-12-05 | 2022-12-11 | 2022-12-05 | 2022-12-11 |  | 5 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | ftr | entr
7.1 | Complete Project Summary | Do the project summary for this project (video or write-up). Includes lessons learned. | None | Everyone | 100% | 2022-12-05 | 2022-12-08 | 2022-12-05 | 2022-12-08 |  | 4 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
7.2 | Complete Final Deliverable | Complete everything related to the final deliverable. | 7.1 | — | 100% | 2022-12-08 | 2022-12-10 | 2022-12-05 | 2022-12-10 |  | 5 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
7.2.1 | Invite Teacher | Invite the teacher to the Discord, code repository, and document repository. | None | Ryan | 100% | 2022-12-08 | 2022-12-10 | 2022-12-05 | 2022-12-05 | -6 | 1 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
7.2.2 | Verify Documents Up-To-Date | Verify all created documents from the previous stages are up-to-date in the repositories. | None | Everyone | 100% | 2022-12-08 | 2022-12-10 | 2022-12-05 | 2022-12-08 | -3 | 4 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
7.2.3 | Verify Zip File | Verify that all information is included in the zip file. | None | Everyone | 100% | 2022-12-08 | 2022-12-10 | 2022-12-08 | 2022-12-10 |  | 2 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
7.2.4 | Turn Zip File Into DropBox | Submit the completed project to the DropBox. | 7.2.1, 7.2.2, 7.2.3 | Ryan | 100% | 2022-12-10 | 2022-12-10 | 2022-12-10 | 2022-12-10 |  | 0 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
7.3 | Complete Final Peer Review | Complete and turn in the peer review for this part. | 7.2 | Everyone | 100% | 2022-12-10 | 2022-12-11 | 2022-12-11 | 2022-12-11 |  | 0 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
Credit for template: https://www.smartsheet.com/content/gantt-chart-templates-dependencies
Formulas:
Programming Pangolins = MIN([Programming Pangolins, row below]:H17)
SCHEDULED FINISH = MAX([SCHEDULED FINISH, row below]:I17)
ACTUAL START = MIN([ACTUAL START, row below]:J17)
ACTUAL FINISH = MAX([ACTUAL FINISH, row below]:K17)
FINISH VARIANCE = IF(AND(AND(NOT(ISBLANK([SCHEDULED FINISH])),NOT(ISBLANK([ACTUAL FINISH]))),[SCHEDULED FINISH]<>[ACTUAL FINISH]),NETWORKDAYS([SCHEDULED FINISH],[ACTUAL FINISH])-1,"")
DURATION in days = NETWORKDAYS([ACTUAL START],[ACTUAL FINISH])
MILESTONE 1:
Finish Planning Stage
MILESTONE 3:
Finish Design Phase
MILESTONE 2:
Finish Analysis Stage
MILESTONE 4:
Turn in a fully, functional project (and party)!

## Roles
Role | Assigned
Project Manager | Ryan Porter
Lead Tester(s) | Evan Slominski | Brooks Robinson
Technical Writer/Scribe | Brooks Robinson
UI Designer | Evan Slominski
Database Manager | Blake Humes
Report Manager | Ryan Porter
Business Advisor | Ryan Porter
Head Programmer/Technical lead | Blake Humes